## Summary
Cycle 3 | Start Date | 2021-07-05 | End Date | 2021-07-17 |  | 10
|  | Execution Details | [8 empty] | # Bug Regression
| Functionality | New Stories - Test Cases | [6 empty] | Pass Rate |  | Pre Reg
|  | Passed | Failed | Yet To Execute | Skipped | % Executed | % Skipped | % Pending |  |  | Registration
| Pre Reg | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | Admin
| Registration | 0 | 0 | 46 | 0 | 0% | 0% | 100% | #DIV/0! |  | IDA
| Admin | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | PMS
| IDA | 69 | 2 | 0 | 0 | 100% | 0% | 0% | 97.18% |  | Resident
| PMS | 49 | 13 | 0 | 0 | 100% | 0% | 0% | 79.03%
| Resident | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Overall | 118 | 15 | 46 | 0 | 74.3% | 0% | 25.7% | 88.72%
179
**** These are new story specific test cases
**** Count doesn't include bug verification
| API Automation | [5 empty] | UI Automation |  |  | DSL Automation
| Module | Total Case | Passed | Failed | Pass % |  | RegClient
| Admin | [5 empty] | Pre Reg
IdRepo
PMS
PreReg
Resident
IDA(Cont.)

## PreReg
Story ID | TestCase_No | Module | Type | Feature | Scenario | Expected Result | Test Result | Tester | Date Tested | Bug ID | Comments
MOSIP-13822 | MOSIP-13822-01 | Pre Registration | functional | Enabling Captcha Service. | In the mosip config - > pre-registration-mz.properties: Set the mosip.preregistration.captcha.enable=true Run the Pre registration services. Open the Login page. | Captcha should appear with I'm not a robot checkbox.
| MOSIP-13822-02 | Pre Registration | functional | Disabling Captcha Service. | In the mosip config - > pre-registration-mz.properties: Set the mosip.preregistration.captcha.enable=false Run the Pre registration services. Open the Login page. | Captcha should not appear.
| MOSIP-13822-03 | Pre Registration | functional | Captcha Service with phone number as user id. | Open the Login page. Enter the user id as phone number. Do not select the I'm not a robot checkbox. Click on send OTP. | Send OTP should be disabled.
| MOSIP-13822-04 | Pre Registration | functional | Captcha Service with email as the user id. | Open the Login page. Enter the user id as email id. Do not select I'm not a robot checkbox. Click on send OTP. | Send OTP should be disabled.
| MOSIP-13822-05 | Pre Registration | functional | Captcha Service with different login language. | Open the Login page. Change the login language. Enter the user id. Do not select I'm not a robot checkbox. Click on send OTP. | Send OTP should be disabled.
| MOSIP-13822-06 | Pre Registration | functional | Captcha Service | Open the Login page. Enter the user id as phone number. Select I'm not a robot checkbox/verify puzzle. | Send OTP should get enabled. Upon entering valid OTP, user should be logged into the system.
| MOSIP-13822-07 | Pre Registration | functional | Captcha Service | Open the Login page. Enter the user id as email id. Select I'm not a robot checkbox/ verify puzzle. | Send OTP should get enabled. Upon entering valid OTP user should be logged into the system.
| MOSIP-13822-08 | Pre Registration | functional | Captcha Service | Open the Login page. Enter the user id. Select Im not a robot check box . If puzzle opens up-> Mismatch the puzzle. | Repeated puzzle should get displayed wihout letting the user log in. It will behave as designed by google.
| MOSIP-13822-09 | Pre Registration | functional | Captcha Service | Open the Login page. Enter the user id. Select I'm not a robot checkbox. Do not click on Send OTP.(Time verification) | "Verification expired, Click the checkbox again" message should be displayed. Message displayed only in English.
| MOSIP-13822-10 | Pre Registration | functional | Captcha Service | Open the Login page. Enter the user id. Select I'm not a robot checkbox. Try to deselect the checkbox. | There should be no option to deselect the checkbox.
| MOSIP-13822-11 | Pre Registration | functional | mosip.preregistration.secret.* property | Open the Login page. Enter the user id. Select I'm not a robot checkbox. Right click on the page and click on inspect. Click on Application - >Storage -> Local storage -> select the testing environment (Ex:qa2.mosip.net).->Config | mosip.preregistration.secret. Property should not be displayed. note: The list of properties passed to the UI are displayed.
MOSIP_14324 | TC_MOSIP_14324-01 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3. Verify the date picker component in Demographic page. Note : Configure the control type as ageDate in the UI spec. | The Date picker should be used for capturing the date of birth value in the demographic page
| TC_MOSIP_14324-02 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3. Verify the spinner component in Demographic page. Note : Configure the control type as ageDate in the UI spec. | The Spinner component should be used to capture the age field in the demographic page.
| TC_MOSIP_14324-03 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3. Verify by clicking on date picker. | On clicking the date picker icon, a date picker calendar should open up.
| TC_MOSIP_14324-04 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3. Verify by clicking on date picker. 4. Verify choosing the date on the calendar. | The user should be able to select a date in the calendar. After selecting the date the same should get displayed in the date field.
| TC_MOSIP_14324-05 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3.Verify the manual entry of the date in the date of birth field. | The user should be allowed to enter a date manually on the date following the date format DD/MM/YYYY. If the age spinner component is configured in the UI spec, the age should get auto displayed wrt the entered date.
| TC_MOSIP_14324-06 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3.Verify the manual entry of the date with : special characters characters negative numbers | The user should be displayed with the invalid date of birth message.
| TC_MOSIP_14324-07 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3.Verify choosing the future date on the calendar. | The user should be displayed with the invalid date of birth message. The future dates should be greyed out.
| TC_MOSIP_14324-08 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3.Verify the manual entry of the age field with the numeric value. | The user should be allowed to enter the numeric value only for age field manually.
| TC_MOSIP_14324-09 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3.Verify the manual entry of the age with special characters characters negative numbers | The user should be displayed with the invalid date of birth message.
| TC_MOSIP_14324-10 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3.Verify the spinner behaviour. | The user should be allowed to increase and decrease the numbers on the date spinner by clicking the up and down arrows. The DOB should get displayed according to the age value selected.(1/1/yyyy)
| TC_MOSIP_14324-11 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Click on Create new application . 3. Create a new application with the date picker or spinner component in demographic page. 4. Click on Continue. | User should be able to enter the date of birth or age and proceed to Documents upload page successfully.
| TC_MOSIP_14324-12 | Pre registration | functional | Date spinner and picker. | 1. Login to Pre reg. 2. Select an application in Pending status/incomplete application status. 3. Modify an application with the date picker and spinner component. 4. Navigate to the next page by clicking on continue. | User should be able to edit a created application using the date picker and spinner and navigate to the Documents upload page successfully.
| TC_MOSIP_14324-13 | Pre registration | functional | Date spinner and picker. | Verify the usage of the Date picker and spinner component works on different browsers. 1. Login to Pre reg. 2. Click on Create new application. 3. Create a new application with the date picker or spinner component in demographic page. 4. Click on Continue. | User should be able to utilize the date picker and spinner on various browsers (chrome/edge/mozilla firefox) and successfully create the application.
| TC_MOSIP_14324-14 | Pre registration | functional | Date spinner and picker. | Verify the usage of the Date picker and spinner component works on different browsers. 1. Login to Pre reg. 2. Select an application in Pending status/incomplete application status. 3. Modify an application with the date picker and spinner component. 4. Click on Continue. | User should be able to utilize the date picker and spinner on various browsers (chrome/edge/mozilla firefox) and successfully edit the application. User should be able to edit the date fields in the created application.
| TC_MOSIP_14324-15 | Pre registration | functional | Date spinner and picker. | Verify the usage of the Date picker and spinner component works on different environments: 1. Single langauage environment. 2. 2 language environment. 3. 3 language environment. | User should be able to utilize the date picker and spinner on various browsers (chrome/edge/mozilla firefox) and successfully create and edit the application. User should be able to edit the date fields in the created application.
| TC_MOSIP_14324-16 | Pre registration | functional | Date spinner and picker. | change the locale field and verify. Locale file → https://github.com/mosip/artifactory-ref-impl/blob/develop/artifacts/src/i18n/pre-registration-i18n-bundle/i18n/default.json | The locale selected should reflect the date format in the demographic page.
MOSIP-15629 | MOSIP-15629-01 | Pre Registration | UI | Consent pop up readibility. | Login to Pre reg. Click on Create new application. Choose the language. View the Consent pop up. | The Consent pop up should be neatly aligned without any extra space. below the accept and submit buttons.
MOSIP-15643 | MOSIP-15643-01 | Pre Registration | UI | Verification message for Recaptcha in login. | In the login page, choose the language. Enter the user id. Click on "Im not a Robot". Do not click on Send OTP. | The "Verification failed. Please check the check box" message should be displayed. The message should be displayed properly without getting trimmed.
MOSIP-15647 | MOSIP-15647-01 | Pre Registration | functional | Send OTP feature. | 1. Open Pre reg login page. 2. Enter the user id. 3. Select the checkbox "I'm not a robot" 4. Click on Send OTP. | Send OTP should get disabled after the first click.

## Registration
Story ID | TestCase_No | Module | Type | Feature | Scenario | Expected Result | Prerequisite | Test Result | Tester | Date Tested | Bug ID | Comments
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Infant applicant. | introducer/Guardian should be added for infant applicant. | 1. Registration_New Flow. 2. Demographic details screen age 4 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian details to capture. | introducer/Guardian details should be captured as mentioned below: 1. Name 2. RID/UIN | 1. Registration_New Flow. 2. Demographic details screen age 4 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify biometric taken for Infant applicant. | Only Face should be captured. | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processing in RegProc. | Packet should go for Introducer Validation stage. | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be success. 2. Packet should process to next stage. | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be Failed. 2. Packet should not process to next stage. | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is Invalid/Not available. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Bio dedupe stages. | Bio dedupe stages should process only with Face. | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processed for UIN generation stage. | Packet should be processed for UIN generation stage | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Infant applicant details sent to ID Repository. | Infant applicant details should be sent to ID Repository. | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Introducer details sent to ID Repository. | Introducer details should not be sent to ID Repository | 1. Registration_New Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Infant applicant. | introducer/Guardian should be added for infant applicant. | 1. Registration_New Flow. 2. Demographic details screen age 5 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian details to capture. | introducer/Guardian details should be captured as mentioned below: 1. Name 2. RID/UIN | 1. Registration_New Flow. 2. Demographic details screen age 5 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify biometric taken for Infant applicant. | Only Face should be captured. | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processing in RegProc. | Packet should go for Introducer Validation stage. | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be success. 2. Packet should process to next stage. | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be Failed. 2. Packet should not process to next stage. | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is Invalid/Not available. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Bio dedupe stages. | Bio dedupe stages should process only with Face. | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processed for UIN generation stage. | Packet should be processed for UIN generation stage | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Infant applicant details sent to ID Repository. | Infant applicant details should be sent to ID Repository. | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Introducer details sent to ID Repository. | Introducer details should not be sent to ID Repository | 1. Registration_New Flow. 2. Demographic details screen age 5 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Infant applicant. | introducer/Guardian should be added for Minor applicant. | 1. Registration_New Flow. 2. Demographic details screen age 6 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian details to capture. | introducer/Guardian details should be captured as mentioned below: 1. Name 2. RID/UIN | 1. Registration_New Flow. 2. Demographic details screen age 6 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify biometric taken for Infant applicant. | All biometrics captured for Minor applicant. | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processing in RegProc. | Packet should go for Introducer Validation stage. | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be success. 2. Packet should process to next stage. | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be Failed. 2. Packet should not process to next stage. | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is Invalid/Not available. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Bio dedupe stages. | Bio dedupe stages should process only with all biometrics as policy defined. | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processed for UIN generation stage. | Packet should be processed for UIN generation stage | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Infant applicant details sent to ID Repository. | Infant applicant details should be sent to ID Repository. | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Introducer details sent to ID Repository. | Introducer details should not be sent to ID Repository | 1. Registration_New Flow. 2. Demographic details screen age 6 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is valid. 6. Policy defined for 'Face', 'Finger' and 'IRIS' 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Infant applicant. | introducer/Guardian should be added for Minor applicant. | 1. Registration_New Flow. 2. Demographic details screen age 7 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian details to capture. | introducer/Guardian details should be captured as mentioned below: 1. Name 2. RID/UIN | 1. Registration_New Flow. 2. Demographic details screen age 7 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Infant applicant. | introducer/Guardian should be added for Minor applicant. | 1. Registration_New Flow. 2. Demographic details screen age 16 3. Minor applicant | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian details to capture. | introducer/Guardian details should be captured as mentioned below: 1. Name 2. RID/UIN | 1. Registration_New Flow. 2. Demographic details screen age 16 3. Minor applicant | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Infant applicant. | introducer/Guardian should be added for Minor applicant. | 1. Registration_New Flow. 2. Demographic details screen age 17 3. Minor applicant | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian details to capture. | introducer/Guardian details should be captured as mentioned below: 1. Name 2. RID/UIN | 1. Registration_New Flow. 2. Demographic details screen age 17 3. Minor applicant | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer/Guardian added for Adult applicant. | introducer/Guardian should not be added for Adult applicant. | 1. Registration_New Flow. 2. Demographic details screen age 18 3. Adult applicant. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify biometric taken for Adult applicant. | All biometrics captured for Adult applicant. | 1. Registration_New Flow. 2. Demographic details screen age 18 3. Adult applicant. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processing in RegProc. | Packet should not go for Introducer Validation stage. | 1. Registration_New Flow. 2. Demographic details screen age 18 3. Adult applicant. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Bio dedupe stages. | Bio dedupe stages should process with all biometrics as policy defined. | 1. Registration_New Flow. 2. Demographic details screen age 18 3. All biometrics captured in biometric screen. 4. Policy defined for all biometrics. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify packet processed for UIN generation stage. | Packet should be processed for UIN generation stage | 1. Registration_New Flow. 2. Demographic details screen age 18 3. All biometrics captured in biometric screen. 4. Policy defined for all biometrics. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify Adult applicant details sent to ID Repository. | Adult applicant details should be sent to ID Repository. | 1. Registration_New Flow. 2. Demographic details screen age 18 3. All biometrics captured in biometric screen. 4. Policy defined for all biometrics. 7. Packet processed for UIN generation stage. | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify below details 1.introducer/Guardian biometric details. 2. Infant Applicant biometric required. | Verify below details 1.introducer/Guardian all biometric should be captured.. 2. Infant Applicant only Face should be captured for biometric. | 1. Registration_Update Flow. 2. Select DOB, Biometric and Guardian check box. 3. DOB added is 4 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify below details 1.introducer/Guardian biometric details. 2. Infant Applicant biometric required. | Verify below details 1.introducer/Guardian all biometric should be captured.. 2. Infant Applicant only Face should be captured for biometric. | 1. Registration_Update Flow. 2. Select DOB, Biometric and Guardian check box. 3. DOB added is 5 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify below details 1.introducer/Guardian biometric details. 2. Infant Applicant biometric required. | Verify below details 1.introducer/Guardian all biometric should be captured.. 2. Infant Applicant only Face should be captured for biometric. | 1. Registration_Update Flow. 2. Select DOB, Biometric and Guardian check box. 3. DOB added is 19 | Pending | Basawa
MOSIP-13115 |  | RegClient |  | AgeGroup_Rules | Verify introducer authentication in Introducer Validation stage.. | 1. Introducer Validation should be Failed. 2. Packet should not process to next stage. | 1. Registration_Update Flow. 2. Demographic details screen age 4 3. Introducer/Guardian details captured. 4. Only face captured in biometric screen. 5. Introducer is Invalid/Not available. | Pending | Basawa
MOSIP-13091 |  | RegClient |  | Biometricsquality | Login to MinIO and verify packet | Tag should be displayed as Biometric_Quality-Iris | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture iris- 44, 30, 50 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | 1. Login to MinIO and verify packet 2. Downlaod the Biometric_Quality-iris and verify tag value. | Tag value should be Average | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture iris- 44, 30, 50 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | Login to MinIO and verify packet | Tag should be displayed as Biometric_Quality-Face | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture face- 44, 30, 50 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | 1. Login to MinIO and verify packet 2. Downlaod the Biometric_Quality-iris and verify tag value. | Tag value should be Poor | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture iris- 10, 10, 10 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | Login to MinIO and verify packet | Tag should be displayed as Biometric_Quality-Left Hand | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture Left Hand- 44, 30, 50 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | 1. Login to MinIO and verify packet 2. Downlaod the Biometric_Quality-Left Hand and verify tag value. | Tag value should be Poor | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and captureLeft Hand 10, 10, 10 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | Login to MinIO and verify packet | Tag should be displayed as Biometric_Quality-Right Hand | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture Right Hand- 44, 30, 50 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | 1. Login to MinIO and verify packet 2. Downlaod the Biometric_Quality-Right Hand and verify tag value. | Tag value should be Poor | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture Right Hand 10, 10, 10 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | Login to MinIO and verify packet | Tag should be displayed as Biometric_Quality-Thumb | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture Thumb- 44, 30, 50 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | 1. Login to MinIO and verify packet 2. Downlaod the Biometric_Quality-Thumb and verify tag value. | Tag value should be Poor | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture Thumb 10, 10, 10 3. Process the packet
MOSIP-13091 |  | RegClient |  | Biometricsquality | Verify Quality Classifier Stage | Quality Classifier Stage should be displayed | 1. Configure Propertiesmosip.regproc.quality.classifier.tagging.quality.ranges={'Poor':'0-29','Average':'30-69','Good':'70-100'} with [Threshold 40] 2. Navigate to biometric screen and capture Thumb 10, 10, 10 3. Process the packet and verify the Quality Classifier Stage.

## Admin
Story ID | TestCase_No | Module | Type | Feature | Scenario | Expected Result | Test Result | Tester | Date Tested | Bug ID | Comments

## IDA
Story ID | TestCase_No | Module | Type | Feature | Scenario | Expected Result | Test Result | Tester | Date Tested | Bug ID | Comments
MOSIP-11464 | IDA_Credential_01 | IDA | Credential | Smoke | When the credential is issued to IDA , it should notify the credential service to make status as "STORED" but it remains in ISSUED state. Create UIN | Both the table should have the status as stored under the credential_transaction and ida.credential_event_store table. | Pass
| IDA_Credential_02 | IDA | Credential | Functional | When Credential issuance to IDA failed as "FAILED_WITH_MAX_RETRIES" it should notify the credential service to make status as "Failed" but it remains in ISSUED state. 1) Bring down IDA 2) Generate UIN , credential will be issued 3) Bring down data share service 4) Bring up IDA | Under credential transaction table after the retry count is over the credential_transaction will have the FAiled as status and rety cout as maximum count specified | Pass
| IDA_Credential_03 | IDA | Credential | Functional | Verify the retry count when retry limit is exceeded 1) Bring down IDA 2) Generate UIN , credential will be issued 3) Bring down data share service 4) Bring up IDA | As data share is down , IDA will keep trying to hit datashare and get the details based on the config | Pass
MOSIP-15206 | IDA_Auth_1 | IDA | Auth | Smoke | To verify the property of Domain under id-authentication-mz.properties | The user should see the property as mosip.ida.allowed.domain.uris=https://dev.mosip.net,https://qa2.mosip.net | Pass
| IDA_Auth_2 | IDA | Auth | Smoke | To Add Value under mosip.ida.allowed.domain.uris= qa1.mosip.net, try to do auth with it | The Auth should be successful | Pass
| IDA_Auth_3 | IDA | Auth | Functional | To remove Value under mosip.ida.allowed.domain.uris= qa1.mosip.net, try to do auth with it | The Auth should be unsuccessfull | Pass |  |  |  | MOSIP-15280
| IDA_Auth_4 | IDA | Auth | Functional | To verify the property of domain by providing space in Auth req | The Auth should be unsuccessfull | Pass
| IDA_Auth_4 | IDA | Auth | Functional | To verify the property of domain by not providing data in Auth req | The Auth should be unsuccessfull | Pass
|  | IDA |  |  | To verify that the individualBiometrics attribute name configurable in Id Auth | Under id-authentication MZ property, retaed property to make the individual biometric as configurable
|  | IDA |  |  | 1)Change the Value of "attributeName" for individual biometric under data share for mpolicy-default-auth 2) The UIN needs to be created to issue new credential | If the name change as configured the auth wll fail
|  | IDA |  |  | Change the value under configuration individualBiometrics attribute
IDA
IDA
IDA
MOSIP-14738 |  | IDA | InternalAuth |  | Create internal Auth request, check the request >> biometrics data should not be encrypted | The data should be in normal form so that IDA doesnot have to decrypt it | Pass
|  | IDA | InternalAuth |  | Check for the requestHMAC under Created Internal Auth request | The requestHMAC should be null | Pass
|  | IDA | InternalAuth |  | Try to perform the New Internal auth a)Create internal Auth request b)Copy Signature from response header c) Paste the Signature under internal Auth request Header | The internal Auth should now take Signature in Header and also have response Signature attached in response | Pass
|  | IDA | InternalAuth |  | Verify the change is URL for internal Auth | The internal auth request ur should be changed from {{url}}/idauthentication/v1/internal/auth to {{url}}/idauthentication/v1/internal/verifyidentity | Pass
|  | IDA | InternalAuth |  | To perfrom internal Auth by adding ida-internal.cert | The Auth should be successful | Pass
|  | IDA | InternalAuth |  | To perfrom internal Auth without adding ida-internal.cert | The Auth should be Failed | Pass
|  | IDA | InternalAuth |  | To Perform old internal auth a)Create internal Auth request b) Perform internal Auth | The Auth should be successful and response Header should contain the Signature | FAIL
MOSIP-15210 |  | IDA | individualBiometrics |  | To change the individualBiometrics attribute name in Datashare as below and try to perform the Bio Auth "attributeName":"individualBiomet", "source": [{ "attribute": "individualBiometrics"}] | The Auth should as the Bimetric attribute doesnot match with the config mosip.ida.credential.biometric.attribute.name under id-authentication-mz.properties file | Pass
|  | IDA | individualBiometrics |  | To change the individualBiometrics attribute name in Datashare as below and try to perform the Bio Auth ""attributeName"":""individualBiomet"", ""source"": [{ ""attribute"": ""individualBiometrics""}]" Also make the property mosip.ida.credential.biometric.attribute.name under id-authentication-mz.properties file as individualBiomet | The Auth should be successfull as the attribute name match with what is there in the property file. | FAIL |  |  | MOSIP-15668
|  | IDA | individualBiometrics |  | Make the property mosip.ida.credential.biometric.attribute.name under id-authentication-mz.properties file as individualBiomet and try to do Auth | The Auth should as the Bimetric attribute doesnot match with the config mosip.ida.credential.biometric.attribute.name under id-authentication-mz.properties file | Pass
MOSIP-15190 |  | IDA | Auth | Functional | To perform Auth using the UIN with the length its generated as set under the kernel properties | The Auth should be successfull. | Pass
|  | IDA | Auth | Functional | To perform Auth using the UIN with the length greated than as set under the kernel properties | The error message should be populated to use correct UIN | Pass
MOSIP-11851 |  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Activate ID when the mpartner-default-auth/CREDENTIAL_ISSUED is Success | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Activate ID when the mpartner-default-auth/DEACTIVATE_ID : Success | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Activate ID when the [{"errorCode":"IDA-MLC-009","errorMessage":"Invalid Input Parameter - id_hash"}] is received | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Authentication Request when the logdesc is authenticateApplicant status : true | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Authentication Request when the logdesc is [{"errorCode":"IDA-MLC-019","errorMessage":"bio-Iris Auth Type is Locked for the UIN"}] | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check Audit log when reuest is sent after 30min for eventname as Authentication Request and log desc : [{"errorCode":"IDA-MLC-001","errorMessage":"Request to be received at MOSIP within 30 minutes","actionMessage":"Please send the request within 30 minutes"}] | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check Audit log when Auth fail due to Face Lock and eventname as Authentication Request , Log Desc : [{"errorCode":"IDA-MLC-019","errorMessage":"bio-FACE Auth Type is Locked for the UIN"}] | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check Audit log when Auth fail due to demo Lock and eventname as Authentication Request , Log Desc : [{"errorCode":"IDA-MLC-019","errorMessage":"bio-FACE Auth Type is Locked for the UIN"}] | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check Audit log when Auth fail due to UIN not available in database and eventname as Authentication Request , | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Authentication Request when the logdesc is authenticateApplicant status : false | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check Audit log for VID and eventname as Authentication Request | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Credential Issued and Log desc as Stored | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Credential Issued and Log desc as Failed | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as eKYC Request and Log Desc kycAuthentication status : true | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as eKYC Request and Log Desc has error message and error code | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Internal Authentication Request for auth as True | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Internal Authentication Request for auth as false | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Internal Authentication Request for auth failed due to error | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname asInternal OTP Request for request as True | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname asInternal OTP Request for request as False | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname asInternal OTP Request for request failed due to UIN not in DB/innumerous attempt and other error message | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as OTP Request for request as True | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as OTP Request for request as False | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as OTP Request for request failed due to UIN not in DB/innumerous attempt and other error message | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Retrieve Auth Transaction History Request | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | IDA | Auditlog | Functional | Check for Audit logdesc for eventname as Update Auth Type Status Request | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as CANCEL_CREDENTIAL_REQUEST | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as CREATE_DRAFT_REQUEST_RESPONSE for Publish/create/update draft request and other erro | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as CREATE_IDENTITY_REQUEST_RESPONSE | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as CREATE_VID | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as CREATE_CREDENTIAL_REQUEST | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as UPDATE_VID_STATUS | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as UPDATE_IDENTITY_REQUEST_RESPONSE | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as UPDATE_AUTH_TYPE_STATUS_REQUEST_RESPONSE | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as RETRY_CREDENTIAL_REQUEST | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as RETRIEVE_VID_UIN | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as RETRIEVE_IDENTITY_REQUEST_RESPONSE_UIN | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as REGENERATE_VID | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as REACTIVATE_VID | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as HAS_DRAFT_REQUEST_RESPONSE | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as GET_DRAFT_REQUEST_RESPONSE | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
|  | ID_REPO | Auditlog | Functional | Check for Audit logdesc for eventname as DEACTIVATE_VID | The log should not contain user sensitive details as UIN, DOB, NAME, UserName, Password, Zipcode | Pass
MOSIP- 7333 |  | IDA | Auth | Functional | Verify that Bio-Type value as Finger | The Auth Should be successfull as Bio-Type value FIR changed to Finger | Pass
|  | IDA | Auth | Functional | Verify that Bio-Type value as Iris | The Auth Should be successfull as Bio-Type value IIR changed to Iris | Pass
|  | IDA | Auth | Functional | Verify that Bio-Type value as Face | The Auth should be success | Pass
|  | IDA | Auth | Functional | Verify the Auth with Bio-Type value as FIR | The Auth should not be success | Pass
|  | IDA | Auth | Functional | Verify the Auth with Bio-Type value as IIR | The Auth should not be success | Pass
|  | IDA | Auth | Functional | Try to Auth when the "bioType": "Iris" and ""digitalId.type": "Iris" | The Auth should be success | Pass
|  | IDA | Auth | Functional | Try to Auth when the "bioType": "is invalid" and ""digitalId.type": "is valid" | The Auth should Fail | Pass
|  | IDA | Auth | Functional | Try to Auth when the "bioType": "is valid" and ""digitalId.type": "is invalid" | The Auth should Fail | Pass
|  | IDA | Auth | Functional | Verify the request body containing for field under digitalId | The Section should contain the field deviceSubType not subType | Pass
|  | IDA | Auth | Functional | Auth UI to support Trust Validation | The Auth UI should work as expected with all the modalities and
MOSIP- 7333

## PMS
Story ID | TestCase_No | Module | Type | Feature | Scenario | Expected Result | Test Result | Tester | Date Tested | Bug ID | Comments
| PMS_01 | PMS | Smoke | MISP | A MISP_PARTNER should be able to create a MISP Partner ("partnerType": "MISP_Partner") | Misp partner must be created with "status": "InProgress" | Pass | Jane
| PMS_02 | PMS | Regression | MISP | Update MISP while inProgress state | Should not be able to update the partner , "message": "Partner is not active." | Pass | Jane
| PMS_03 | PMS | Smoke | MISP | Upload partner certificate for the MISP | Misp partner should have "status": "Approved" | Pass | Jane
| PMS_04 | PMS | Regression | MISP | Update MISP while in approved state using the MISP_Partner role | Should be able to update | Fail | Jane |  | MOSIP-15903
| PMS_05 | PMS | Regression | MISP | A MISP_Partner should be able to retrieve his details | Should be able to retrieve MISP partner data | Fail | Jane |  | MOSIP-15903
| PMS_06 | PMS | Smoke | MISP | Generate MISP license key with the MISP_Partner role | MISP license should be generated and license status should be Active | Fail | Jane |  | MOSIP-15833
| PMS_07 | PMS | Smoke | MISP | View the generated MISP license with the MISP_Partner role | MISP_Partner should be able to get the license | Fail | Jane |  | MOSIP-15903
| PMS_08 | PMS | Regression | MISP | Verify the length of the generated license key | Length should be 50 as per the default config, mosip.kernel.idgenerator.misp.license-key-length = 50 | Pass | Jane
| PMS_10 | PMS | Regression | MISP | Verify the MISP License validity | It should be 360 days as per the default config mosip.pmp.misp.license.expiry.period.indays = 360 | Pass | Jane
| PMS_12 | PMS | Regression | MISP | Verify whether MISP_Partner can activate/de activate MISP license key | Should be able to activate/deactivate license keys | Pass | Jane
| PMS_13 | PMS | Regression | MISP | Verify whether PARTNER_ADMIN can activate/de activate MISP partner | Should be able to activate/deactivate MISP Partner | Pass | Jane
| PMS_14 | PMS | Regression | MISP | Update MISP partner while in deactivated state | Should not be able to update MISP details | Pass | Jane
| PMS_15 | PMS | Integration | MISP-Auth | Perform Auth with a valid MISP | Should be able to perform auth | Pass | Jane
| PMS_16 | PMS | Integration | MISP-Auth | Perform Auth with a deactivated MISP | Should not be able to perform auth | Pass | Jane
| PMS_17 | PMS | Integration | MISP-Auth | Perform Auth with an expired MISP license | Should not be able to perform auth | Pass | Jane
| PMS_18 | PMS | Integration | MISP-Auth | Perform Auth with a deactive MISP license | Should not be able to perform auth | Pass | Jane
| PMS_19 | PMS | Smoke | Policy | Policy manager to create a new policy group | Policy group should be created with "is_Active": true | Pass | Jane
| PMS_20 | PMS | Regression | Policy | Deactivate a policy group | Policy group should become inactive and the associated policies must also become inactive | Pass | Jane
| PMS_21 | PMS | Regression | Policy | Create policies under a deactivated group | Should not be able to create policies. | Fail | Jane |  | MOSIP-15819
| PMS_22 | PMS | Regression | Policy-Auth | Deactivate a policy group and perform auth with its associated policy | Auth should fail | Fail | Jane |  | MOSIP-15841
| PMS_23 | PMS | Smoke | Policy | Policy manager to create an auth policy with allowed auth types and allowed kyc attributes | Policy should be created with "is_Active": false | Pass | Jane
| PMS_24 | PMS | Regression | Policy | Policy manager to update a policy in InProgress state | Policy should get updated and remain in Drafted stage | Fail | Jane |  | MOSIP-15914
| PMS_25 | PMS | Regression | Policy | Policy manager to activate/deactivate a policy in InProgress state | Should not be able to activate/deactivate the policy | Fail | Jane |  | MOSIP-15916
| PMS_26 | PMS | Smoke | Policy | Policy manager to publish a policy | Policy should be published with "status": "PUBLISHED" with an expiry of pmp.policy.expiry.period.indays = 360 | Pass | Jane
| PMS_27 | PMS | Regression | Policy | Policy manager to update a policy in Published state | Policy should get updated and remain in Drafted stage | Pass | Jane
| PMS_28 | PMS | Regression | Policy | Policy manager to activate/deactivate a policy in Published state | Should be able to activate/deactivate a policy . If deactivated policy should go to Drafted state. | Pass | Jane
| PMS_29 | PMS | Integration | Policy-Auth | Edit the allowed auth types/kyc attributes and perform auth | Should be able to perform auth | Pass | Jane
| PMS_30 | PMS | Smoke | Policy | Policy manager to create a data share policy with shareable attributes | Should be able to create a data share policy | Pass | Jane
| PMS_31 | PMS | Integration | Policy-Auth | Update the shareable attributes and perform auth. | Should be able to perform auth with the specified attributes. | Pass | Jane
| PMS_32 | PMS | Integration | Policy-Auth | Deactivate a policy and perform auth | Auth should fail | Pass | Jane
| PMS_33 | PMS | Smoke | Partner | Verify Partner_Admin/Auth_Partner is able to create a partner | Should be able to create a partner | Fail | Jane |  | MOSIP-15944
| PMS_34 | PMS | Regression | Partner | Update Partner while in Progress state | Should not be able to update the partner , "message": "Partner is not active." | Pass | Jane
| PMS_35 | PMS | Regression | Partner | Partner Admin to Deactivate Auth Partner while In Progress state | Should not be able to Deactivate the partner | Fail | Jane |  | MOSIP-15918
| PMS_36 | PMS | Smoke | Partner | Upload partner certificate for the Auth Partner | Auth partner should have "status": "Approved" | Pass | Jane
| PMS_37 | PMS | Regression | Partner | Update Auth Partner while in approved state using the Auth_Partner role | Should be able to update | Pass | Jane
| PMS_38 | PMS | Regression | Partner | An Auth_Partner should be able to retrieve his details | Should be able to retrieve Auth partner data | Fail | Jane |  | MOSIP-15905
| PMS_39 | PMS | Regression | Partner | Partner Admin to Deactivate Auth Partner while in Approved state | Should be able to update | Pass | Jane
| PMS_40 | PMS | Regression | Partner | Update partner details while in deactivated state | Should not be able to update | Pass | Jane
| PMS_41 | PMS | Regression | Partner-Auth | Perform auth with a deactivated partner | Should not be able to do auth | Pass | Jane
| PMS_42 | PMS | Regression | Partner | Map auth policy to a deactivated partner | Should not be able to map | Pass | Jane
| PMS_43 | PMS | Smoke | Partner | Map auth policy to a activated partner - submit api partner key request |  | Pass | Jane
| PMS_44 | PMS | Regression | Partner | Map deactivated policy to auth partner |  | Pass | Jane
| PMS_45 | PMS | Smoke | Partner | Map auth policy to a activated partner - submit api partner key request | Api key request should be sent to partner manager | Pass
| PMS_46 | PMS | Smoke | Partner | Partner admin to approve the api key request | Request should be approved | Pass
| PMS_47 | PMS | Regression | Partner | Partner admin to reject the api key request | Request should be rejected | Pass
| PMS_48 | PMS | Integration | Partner | Perform auth with the approved api key | Should be able to perform auth | Pass
| PMS_49 | PMS | Integration | Partner | Perform auth with the rejected api key | Should not be able to perform auth | Fail |  |  | MOSIP-16001
| PMS_50 | PMS | Regression | Partner | Map the partner to a different policy | Should be able to map | Pass
| PMS_51 | PMS | Regression | Partner | Map the partner to the same policy | Should be able to map with auto approval | Pass
| PMS_52 | PMS | Regression | Partner | Deactivate the api key and map the partner with the same policy | Api key request should be sent to partner manager | Fail |  |  | MOSIP-15953
| PMS_53 | PMS | Regression | Partner | Deactivate the api key and map the partner with a different policy | Api key request should be sent to partner manager | Pass
| PMS_54 | PMS | Integration | Certificate | To add the external certificate for Auth, device and FTM partner and try to do Auth | The Auth should be success | Pass
| PMS_55 | PMS | Integration | Certificate | To add certificate and check that certificates are updated in respective tables | The certificate should be updated in both keymgr & ida.ca_cert_store Table | Pass
| PMS_56 | PMS | Integration | Certificate | To add the certificate for kyc partner and try to do demo and OTP Auth | The Auth should be success | Pass
| PMS_57 | PMS | Integration | Certificate | Add only Auth Partner certificate without adding Device and FTM and try to do Bio Auth | The certificate should be updated in both & ida.ca_cert_store Table, but will fail | Pass
| PMS_58 | PMS |  | Certificate | Upload certificate from a different organization than the one registered | Should not be able to upload the certificate | Pass
| PMS_59 | PMS | Regression | Audit | To verify the audit table for Failure of transcation, Create Policy Group already Created | The Policy Group creation will be failed and Audit table should have entry for the same | Pass
| PMS_60 | PMS | Integration | PartnerData | PMS to push data to IDA, IDA will not pull from PMS | The data created using Partner Management API should be present in IDA database | Pass
| PMS_61 | PMS | Integration | PartnerData | The User should be able to do Auth even the partner service is down as validation is happening from IDA | Auth should happen | Pass
| PMS_62 | PMS | Integration | DataSharePolicy | To mark encrypted as false for email atribute from data share shareableAttributes and perform auth/kyc (Remove email from zero knowledge encrypted values) | Auth should happen. Verify in identity_cache table, email value should not be encrypted. | Pass
| PMS_63 | PMS | Integration | DataSharePolicy | To remove the email attribute from data share shareableAttributes and perform auth/kyc (Keep the attribute in auth policy) | Should not be able to perform auth/ekyc with email | Pass
| PMS_64 | PMS | Integration | DataSharePolicy | To mark encrypted as false for individualBiometrics atribute from data share shareableAttributes and perform bio auth/kyc |  | Pass

## Resident
Story ID | TestCase_No | Module | Type | Feature | Scenario | Expected Result | Test Result | Tester | Date Tested | Bug ID | Comments
To verify the Update address withdocument
To verify the Update address without document
To Print the EUIN card in eng and ara
To Print the EUIN card in FRA and ara